## Sheet1
Project Name | Online appointment system for healthcare Organization
Start Date | 2018-10-20
End Date | 2018-12-11
Overall Progress | 20%
Tasks | Responsible | Start | End | Days | Status | 2018-10-20 | 2018-10-21 | 2018-10-22 | 2018-10-23 | 2018-10-24 | 2018-10-25 | 2018-10-26 | 2018-10-27 | 2018-10-28 | 2018-10-29 | 2018-10-30 | 2018-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-17 | 2018-11-18 | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-24 | 2018-11-25 | 2018-11-26 | 2018-11-27 | 2018-11-28 | 2018-11-29 | 2018-11-30 | 2018-12-01 | 2018-12-02 | 2018-12-03 | 2018-12-04 | 2018-12-05 | 2018-12-06 | 2018-12-07 | 2018-12-08 | 2018-12-09 | 2018-12-10 | 2018-12-11
Kick off Discussion | Entire Team | 2018-10-20 | 2018-10-20 | 1 | Complete
Objectives and Scope | Entire Team | 2018-10-21 | 2018-10-25 | 5 | Complete
Initiation
Defining Project Requirements | Entire Team | 2018-10-26 | 2018-10-29 | 4 | Complete
Defining Infrastructure Requirements | Lalit/Arinze | 2018-10-30 | 2018-10-30 | 1 | Complete
Defining Roles and Responsibilities | Entire Team | 2018-10-30 | 2018-10-31 | 2 | Complete
Design
Deciding process flow | Shikhar/Arinze | 2018-11-01 | 2018-11-09 | 9 | Complete
Defining Data Model | Vishwajeet/Lalit | 2018-11-01 | 2018-11-09 | 9 | Complete
Defining UI Layout | Shikhar/Vishwajeet | 2018-11-10 | 2018-11-15 | 6 | Complete
Development
DB Development | Shikhar/Vishwajeet | 2018-11-15 | 2018-11-25 | 11 | Complete
UI Development | Shikhar/Vishwajeet | 2018-11-15 | 2018-11-25 | 11 | Complete
System Integration | Lalit/Arinze | 2018-11-15 | 2018-11-25 | 11 | Complete
Testing | Lalit/Arinze | 2018-11-15 | 2018-11-25 | 11 | Complete
Bug Fixing | Entire Team | 2018-11-26 | 2018-12-02 | 7 | Complete
Development Closure | Entire Team | 2018-12-03 | 2018-12-05 | 3 | Complete
Operations
Configuration and Deployment | Entire Team | 2018-12-06 | 2018-12-07 | 2 | Complete
System Testing | Entire Team | 2018-12-08 | 2018-12-09 | 2 | Complete
Project Closure |  | 2018-12-10 | 2018-12-11